## Sheet1
MIA (Material Information Analytics)
Estimated Timing Plan | [27 empty] | Date Created: 02/07/2019
Phase 1 scope (Masterlists, BOM, Customer Demand, Capacity Forecast, Cost Table, MRP)
Rev No. 2
Developers: Carlo Sotomayor, Paulo Encontro | [27 empty] | Revised Date: 10/01/2019
NO. | CATEGORY | ITEMS TO BE DONE |  | PIC | STATUS | 2019-10-01
[6 empty] | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Report | BOM Report Generation | PLAN | APQP | On-going Trial | 2019-10-01 5: Saturday; 2019-10-01 6: Sunday; 2019-10-01 12: Saturday; 2019-10-01 13: Sunday; 2019-10-01 19: Saturday; 2019-10-01 20: Sunday; 2019-10-01 26: Saturday; 2019-10-01 27: Sunday; 2019-10-01 31: Company Holiday
ACTUAL
2 | Master Data | Other additional master discovered during development | PLAN | MIS | Done
ACTUAL
3 | Data Calculation | Customer Demand | PLAN | MIS, PC | Done
ACTUAL
4 |  | Capacity Forecast FG (Stage 1) | PLAN | MIS, PC | On-going Trial | bar: 2019-10-01 2 to 2019-10-01 4; 2019-10-01 7 to 2019-10-01 11; 2019-10-01 14 to 2019-10-01 18; 2019-10-01 21 to 2019-10-01 25; 2019-10-01 28 to 2019-10-01 30
ACTUAL
5 |  | Cost Table | PLAN | MIS, PC | On-going Development | bar: 2019-10-01 2 to 2019-10-01 4; 2019-10-01 7 to 2019-10-01 11; 2019-10-01 14 to 2019-10-01 15
ACTUAL
6 |  | Capacity Forecast WP (Stage 2) | PLAN | MIS, PC | On-going Development | bar: 2019-10-01 2 to 2019-10-01 4; 2019-10-01 7 to 2019-10-01 11; 2019-10-01 14 to 2019-10-01 18
ACTUAL
7 |  | MRP (Material Resource Planning) | PLAN | MIS, PC | Pending
ACTUAL